## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Discuss and coordinate deliverable objectives as a group. | bar: Day 0; Day 2
2 | Examine freecol source code. | Day 0: 2; Day 2: 0.5; Day 3: 1; Day 4: 0.5
3 | Design use case diagrams. | Day 0: 1.5; Day 4: 1; Day 6: 0.5
4 | Code metrics. | Day 0: 2; Day 4: 0.5; Day 5: 1; Day 6: 0.5
Completed Effort |  | 0 | 0 | 1.5 | 1 | 2 | 1 | 1 | 0
Remaining Effort |  | 6.5 | 6.5 | 5 | 4 | 2 | 1 | 0 | 0
Ideal Burndown |  | 6.5 | 5.5714 | 4.6429 | 3.7143 | 2.7857 | 1.8571 | 0.92857 | 0