## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Review user stories ideas and update them to new ones. | Day 0: 1.5; Day 1: 1.5
2 | Implement User story 1 - reveal map tiles. | 4 | 0.5 | 1 | 0.5 | 2
3 | Implement User story 3 - add gold button. | 4 | 1 | 1 | 0.5 | 1.5
4 | Unitests - User story 1. | Day 0: 3; Day 4: 0.5; Day 5: 1; Day 6: 1.5
5 | Unitests - User story 2. | 3 |  |  |  | 0.5 | 1 | 0.5 | 1
6 | Unitests - User story 3. | Day 0: 3; Day 4: 2; Day 6: 1
7 | Record and edit demo video of implementations. | Day 0: 3; Day 6: 2; Day 7: 1
8 | Report. | 5 | 0.5 |  | 1 | 0.5 | 0.5 | 1.5 | 1
9 | Deliver new user stories. | bar: Day 0; Day 7
Completed Effort |  | 0 | 3.5 | 2 | 2 | 7 | 2.5 | 6.5 | 4
Remaining Effort |  | 27.5 | 24 | 22 | 20 | 13 | 10.5 | 4 | 0
Ideal Burndown |  | 27.5 | 23.5714 | 19.6429 | 15.7143 | 11.7857 | 7.8571 | 3.9286 | 0