## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Divide ourselfs in groups so that our work could be more efficient | bar: Day 0; Day 2
2 | Put our ideas in progress and alter the code | 3 |  |  | 1 | 0.5 | 1 | 0.5
3 | Identify design patterns. (continuation) | Day 0: 0.5
Completed Effort |  | 0 | 0 | 1 | 1 | 0.5 | 1 | 0.5 | 0
Remaining Effort |  | 4.5 | 4.5 | 3.5 | 2.5 | 2 | 1 | 0.5 | 0.5
Ideal Burndown |  | 4.5 | 3.8571 | 3.2143 | 2.5714 | 1.9286 | 1.2857 | 0.64286 | 0