## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Fork and create project repository | bar: Day 0 to Day 1
2 | Understand the fundamentals of the gameplay | Day 0: 3; Day 1: 0.5; Day 2: 2; Day 3: 0.5
3 | Discuss and choose 3 User Stories of three non-trivial extensions to the tool. | Day 0: 4; Day 4: 1.5; Day 5: 0.5; Day 6: 2
4 | Discuss and coordinate deliverable objectives as a group. | bar: Day 0; Day 7
Completed Effort |  | 0 | 1.5 | 2 | 0.5 | 1.5 | 0.5 | 2 | 1
Remaining Effort |  | 9 | 7.5 | 5.5 | 5 | 3.5 | 3 | 1 | 0
Ideal Burndown |  | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0