## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | Fork and create project repository | 1 | 1
2 | Understand the fundamentals of the gameplay | 3 | 0.5 | 2 | 0.5
3 | Search for ideas of desired additional functionalities | 3 |  |  | 1 | 1.5 | 0.5
4 | Discuss and choose 3 User Stories of three non-trivial extensions to the tool. | 2 |  |  |  |  | 1 | 1
Completed Effort |  | 0 | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 1
Remaining Effort |  | 9 | 7.5 | 5.5 | 4 | 2.5 | 1 | 0
Ideal Burndown |  | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0