## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Identify design patterns. | Day 0: 3; Day 1: 1.5; Day 2: 0.5; Day 3: 0.5
2 | Identify code smells. | Day 0: 2; Day 1: 0.5; Day 3: 1; Day 4: 0.5
3 | Discuss and coordinate commits. | bar: Day 0; Day 5
4 | Discuss our code ideas and ways to start implement them. | Day 0: 1.5; Day 6: 0.5; Day 7: 1
| Completed Effort | 0 | 2 | 0.5 | 1.5 | 0.5 | 1 | 0.5 | 1
| Remaining Effort | 7.5 | 5.5 | 5 | 3.5 | 3 | 2 | 1.5 | 0.5
| Ideal Burndown | 7.5 | 6.4286 | 5.3571 | 4.2857 | 3.2143 | 2.1429 | 1.0714 | 0